## Sheet1
ISSUE MANAGEMENT LOG
Project Name: demoblaze
Project Manager Name: Bit68 Team
Tester Name: Ibrahim Fahmy
Company Name: Bit68 |  |  | Tittle | Issue Description | Time stamp | Test Data 01xxxxxxxx | Detected by | AssignTeams | Assign Users | Closed at
Date: 31/5/2025
ID | Title | Description | Precondition | Test Data | Steps to re-produce | Status | Expected Result | Actual resualt | Evidance | Environment | Scenarios | Priority | Severity | Execution By
BUG_001 | Login/Signup allows data entry but fails validation unexpectedly | When the user enters valid login or signup data, the system shows a success message but shortly after returns an error stating the credentials are invalid, preventing the user from accessing the application. | User tries to login or signup with valid credentials | Valid user data (email + password) | 1. Open login or signup page 2. Enter valid data 3. Click "Login" or "Sign Up" 4. System shows message "the email already exist 5. Shortly after shows error message | New | User is successfully logged in or signed up and redirected to the app | System shows temporary success message then fails login with "Invalid credentials" error, blocking access | https://jam.dev/c/37ec86ad-72a3-473a-96fc-287f6b6d541c | macOS (x86) 14.5.0 - Chrome 137.0.7151.56 - 1440x678 | TC_001 – Add product with stock to cart (logged in) | High | Critical | Ibrahim Fahmy
BUG_ADD_TO_CART_GUEST_001 | Guest user can add product to cart without login | When accessing the website as a guest (not logged in), the user can open any product page and click "Add to Cart", which triggers a success popup and adds the product to cart. This violates the expected behavior, where guest users should be prompted to log in before adding products. | User is not logged in (guest mode) | Any product listed on the site | 1. Open website as guest (not logged in) 2 . Navigate to any product page 3. Click the "Add to Cart" button 4. Observe popup/message after click | New | User should be redirected to login page or shown a login prompt before adding product | Product is added successfully and popup/alert confirms "Product added to cart successfully" | https://jam.dev/c/0e04254f-9fe8-4021-97d8-59b45133cf1c | macOS (x86) 14.5.0 - Chrome 137.0.7151.56 - 1440x679 | TC_ADD_TO_CARD_007-Guest User - Cart Access Restriction | High | High | Ibrahim Fahmy